## Sheet1
Phase/Activity | To Check | Control Methods | Time | In Charge | Quality Documentation Criteria
1. Planning | 1.1 Project Scope Determination
| 1.1.1 Project scope determination with the sponsor | Regular meetings with the sponsor | At the beginning of project | Sponsor and Team | Meeting minutes, scope documents
| 1.1.2 Project meetings decisions with sponsor | Documentation of decisions made in meetings | At the beginning of project | Sponsor and Team | Meeting minutes, scope documents
| 1.1.3 Deciding Change management | Change management procedures implementation | At the beginning of project | Sponsor, Team and Mentor | Project charter, updated project plan
| 1.1.4 Budget determination | Budget review and control | Periodic reviews | Sponsor and Team | Scope documents, cost management plans
1.2 Product Scope
| 1.2.1 Product scope determination | Review of product features and functions | At the beginning of work and during the work | Sponsor, Team and Mentor | Product scope document
| 1.2.2 Identifying product features and functions | Verification of identified features and functions | At the beginning of work and during the work | At the beginning of work and during the work | Scope statement
| 1.2.3 Determining the details of the AI tool to be used | Validation of AI tool specifications | At the beginning of work and during the work | Team | Scope statement
1.3 Methodology
| 1.3.1 Planning and creating WBS | WBS review and validation | At the beginning of work and during the work | Sponsor, Team and Mentor | WBS document
| 1.3.2 Deciding on which PM methods will be used | Implementation of selected PM methods | Project initiation | Team | Scope statement
2. Implementation Of The System | 2.1 Data Collection
| 2.1.1 Receiving documents regarding regulations | Document receipt verification | During the project implementation | Sponsor | Bank processes document
| 2.1.2 Gathering regulations From BDKK | Confirmation of regulations gathered | During the project implementation | Team | Regulations document
2.2 ChatGPT Integration
| 2.2.1 Integration of ChatGPT 4.0 | Testing and validation of integration | During the project implementation | Team | Integration results
2.3 Comparison Algorithm
| 2.3.1 Developing algorithm and AI prompts | Algorithm testing and validation | During the project implementation | Team | Algorithm specifications, test results
2.4 System Design
| 2.4.1 Designing the Architecture for the System | Architecture review and validation | During the project implementation | Team | Architecture specifications
2.5 Development of Dashboard
| 2.5.1 Designing dashboard | Dashboard design review and validation | During design implementation | Team | Dashboard design specifications
2.6 Reporting Module
| 2.6.1 Creating Reports | Report creation and validation | During implementation | Team | Report specifications
2.7 User Training and Support
| 2.7.1 Training of the System for Bank employees | Training sessions and support | After implementation | Team and Sponsor Team (Halkbank) | Training materials, support procedures
3. Implementation Analysis | 3.1 System Analysis
| 3.1.1 Analysis of how the system works | System analysis and improvement recommendations | Post-implementation | Team and Sponsor Team (Halkbank) | System analysis report
3.2 Output Analysis
| 3.2.1 Evaluate Success Rate and Failure Points | Evaluation of system outputs and failure points | Post-output analysis | Team | System analysis and evaluation reports
4. System Revision | 4.1 Feedback Analysis
| 4.1.1 Updating the system based on the success rate | Analysis of feedback and implementation of updates | Post-implementation analysis | Team | Updated system documentation
5. Reports | 5.1 Progress Report
| 5.1.1 Creating Summary Reports | Compilation of progress information | Periodic | Team | Progress reports, feedback
5.2 Final Report
| 5.2.1 Reporting of all processes of the project | Compilation of final project information | Project completion | Team | Final project report
6. Presentations | 6.1 Progress Presentation
| 6.1.1 Preparing Presentations about the progress | Presentation preparation and delivery | Periodic | Team | Presentation materials, feedback
6.2 Final Presentation
| 6.2.1 Preparing presentation of the final part of the project | Final presentation preparation and delivery | Project completion | Team | Final presentation materials